# FLOODSENSE: consortium response to the RP1 periodic review report

## Covering text

To: [Project Officer name], [granting authority / unit] Subject: FLOODSENSE (GA [number]): consortium observations on the RP1 review report of [review date]

Dear [Title Surname],

With reference to the periodic review report for reporting period 1 of FLOODSENSE (GA [number]), dated [review date], we send the consortium’s observations within the 30 days requested. We thank the reviewers for their comments.

The report contains four comments requiring action (C1 to C4) and two recommendations (R1, R2). We accept all six. C1, C2 and C3 are addressed in a revised version of D3.2 (KPI values in Section 4, an updated deviation section, and a new data and code availability annex). C4 and R2 are addressed [now, as an annex to this response / in the RP2 periodic report: decisione del consorzio]. R1 is addressed in the RP2 periodic report. The table below gives, for each comment, our position, the change made or planned and where it can be found.

[Revised D3.2 (version [n]) is attached / will be resubmitted by [date: decisione del consorzio].]

[Points to discuss with the PO, if any: decisione del consorzio.]

Kind regards,

[Name Surname] [Role], on behalf of the FLOODSENSE consortium

## Response table

| # | Comment (short quote) | Position | Response | Change and location | Responsible | Deadline |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | “Results are described in qualitative terms only. No KPI baseline or measured value is reported.” | Accepted | Section 4 of D3.2 will report each KPI in DoA Annex 1, Table 3.2 with baseline, target, measured value, period of measurement and source: [KPI 1: baseline, target, measured value, source], [KPI n: …]. Where a KPI has not been measured yet, we state why and when it will be. | D3.2 v[n], Section 4, KPI table [da fare] | [partner / person] | [date] |
| C2 | “MS4 was reported as achieved in month 12 while D3.2 is submitted in month 20.” | Accepted | [Explanation of the relation between MS4 and D3.2: due month of D3.2 in the DoA (M[da DoA]), cause of the [n]-month gap, effect on other tasks and deliverables, corrective action. Decisione del consorzio: whether MS4 is confirmed as achieved at M12 or its status is corrected.] Section 5 is rewritten: the statement that there are no significant deviations is replaced by the description of the D3.2 delay. | D3.2 v[n], Section 5 [da fare] | [partner / person] | [date] |
| C3 | “The data and code availability annex required by the programme is missing.” | Accepted | We add Annex I listing, for each dataset and code produced or used in D3.2: repository, DOI or persistent link, licence and access conditions. [List of datasets and code: to be provided.] | D3.2 v[n], Annex I [da fare] | [partner / person] | [date] |
| C4 | “Dissemination activities listed in the periodic report are limited to conference participation.” | Accepted | [Progress against each dissemination KPI in the DoA: KPI, baseline, target, value at end of RP1, source.] [Activities other than conferences carried out in RP1, if any: publications, datasets, web, end-user events, each with audience reached, outcome and evidence.] [Corrective action for KPIs below target: decisione del consorzio.] | Periodic report RP1 [section to be confirmed] or RP2 report, dissemination section [decisione del consorzio: integrate now or in RP2] | [partner / person] | [date] |
| R1 | “Align the reporting of task progress with the task structure of the DoA.” | Accepted | From RP2 the technical report will describe progress task by task with the DoA codes (T[n].[n]). | RP2 periodic report, Part B Section 1 | [WP leaders] | [RP2 report due date] |
| R2 | “Provide a risk update for the remaining periods.” | Accepted | We will provide an update of each risk in the DoA risk table and of any new risk, with likelihood, mitigation and status. [Decisione del consorzio: send now as annex to this response, or in RP2.] | [Annex to this response / RP2 report, risk section] | [Coordinator] | [date] |

## Follow-up table for the RP2 report

| Recommendation / comment | Action | Status at RP2 | Evidence |
| --- | --- | --- | --- |
| C1 | KPI values in D3.2 Section 4 | [completed / ongoing / not started, with reason] | [D3.2 v[n]] |
| C2 | Deviation section of D3.2 updated | [status] | [D3.2 v[n], Section 5] |
| C3 | Data and code availability annex added | [status] | [D3.2 v[n], Annex I] |
| C4 | Dissemination KPIs reported | [status] | [section] |
| R1 | Task-by-task reporting | [status] | [RP2 Part B] |
| R2 | Risk update | [status] | [annex or section] |

## Notes for the user (in italiano)

Decisioni del consorzio da prendere: 1. C2: MS4 è davvero raggiunta a M12? Qual è il mese di scadenza di D3.2 nella DoA e perché è stato consegnato a M20? 2. C4: integrare la disseminazione nel report RP1 adesso o nel report RP2? 3. R2: mandare l’aggiornamento dei rischi in allegato a questa risposta o nel report RP2? 4. Data di reinvio di D3.2 rivisto.

Possibile amendment: se lo spostamento di D3.2 (o di MS4) supera quanto la DoA consente, valutare con il PO se serve un amendment.

Assunzioni: programma non indicato nel report; formato e riferimenti (“Annex 1”, “periodic review”) sono compatibili con Horizon Europe, ma non è confermato. Mancano la DoA e il D3.2 inviato: tutte le risposte di merito sono segnaposto.