## Slide 1: FLOODSENSE at mid-term: [one-sentence summary of status, e.g. N of M deliverables submitted]
Mid-term review, period M1-M[n]
Notes: Introduce yourself. Say in one sentence where the project stands against the DoA: [overall status].

## Slide 2: For M1-M[n] the DoA planned [n] deliverables and [n] milestones
What the DoA planned for the period
Objectives for the period: [objectives from the DoA]
Expected deliverables: [codes, from the DoA]
Expected milestones: [codes and months, from the DoA]
Notes: Start from the contract, not from the activities: that is what the project officer has in front of them. All codes from the DoA.

## Slide 3: [n] of [n] deliverables submitted, [n] of [n] milestones achieved
Deliverables
[D1.1: submitted M[x]]
[D3.2: submitted M[x], due M[y]]
[...]
Milestones
[MS1: achieved M[x], means of verification]
[MS4: ...]
[...]
Notes: Status table. If anything is late, say so here and refer to the deviations slide.

## Slide 4: 1 — What has been done
Notes: One section per work package, in DoA order.

## Slide 5: WP[n]: [main result of the WP in the period, in one sentence]
[Task T[n].[n]]
[Activity carried out, with task code]
[Output: deliverable, dataset, software, with link or DOI]
[Partners involved]
Notes: Repeat this slide for each WP. Every statement with its task or deliverable code.

## Slide 6: [Measured result: KPI and value, e.g. KPI X reached [value] against a target of [value]]
KPIs for the period
[KPI 1]: baseline [ ], target [ ], measured [ ], source [ ]
[KPI 2]: baseline [ ], target [ ], measured [ ], source [ ]
[KPI 3]: baseline [ ], target [ ], measured [ ], source [ ]
Notes: Only values measured and provided by the consortium. A KPI not yet measured is reported as such, with the expected date.

## Slide 7: [Main evidence: what the figure shows]
What it shows
[Basin, period, events]
[Metric and value]
[Data source]
[Figure or chart]
[to be inserted: figure provided by the consortium]
Notes: One figure only, readable from the back of the room. A caption that says what it shows.

## Slide 8: 2 — Deviations and risks

## Slide 9: [n] deviations from the work plan, with cause and corrective action
Deviations
[Code]: planned M[x], actual M[y]
Cause: [concrete cause]
Effect and action: [effect on other tasks, action, new date, amendment if needed]
Notes: One deviation per table row if there is more than one. Never say 'no significant deviations' without comparing with the DoA dates.

## Slide 10: [Main risk for the second period and how we mitigate it]
Updated risks
[Risk, from the DoA risk register]: likelihood [ ], impact [ ]
Mitigation: [planned measure and status]
[New risk, if any]
Notes: Risks from the DoA register, updated. A new risk is presented as new.

## Slide 11: 3 — Next period

## Slide 12: In M[n+1]-M[end] we will submit [n] deliverables, starting with [code]
Plan
[Deliverable and month, from the DoA]
[Milestone and month, from the DoA]
[Follow-up actions on recommendations, if any]
Notes: Only activities in the DoA or decided by the consortium.

## Slide 13: [Take-home message: project status in one sentence]
[Key message]
[Point 1]
[Point 2]
[Coordinator contact]
Notes: Close with the message, not with 'Thank you'.

## Slide 14: Full table of deliverables and milestones
[Table from the DoA with updated status]
Notes: For detailed questions on status.

## Slide 15: How the KPIs are measured
[For each KPI: metric, data, period, source]
Notes: For questions on how the KPIs were measured.